SPECIFICATION FOR THE

EXTERNAL REPAIR & REDECORATION

OF

RODNEY COURT

### 6 – 8 MAIDA VALE

LONDON W9

## 16 January 2001

PRELIMINARIES

#### PARTICULARS OF CONTRACT

| 0.1 | SITUATION OF WORKS | Rodney Court, 6 – 8 Maida Vale, London W9 |
| --- | --- | --- |
| 0.2 | DESCRIPTION OF WORKS | The Works comprise the overlaying of the existing asphalt roof and external walkways together with the general external repairs and redecoration of the building. |
| 0.3 | EMPLOYER | Rodney Court Management Limited |
| 0.4 | SURVEYOR | Richard Birchall Associates 17 St. Albans Grove Kensington London W8 5BP Tel: 020-7727-9739 Fax: 020-7229-3510 Mobile: 0836-634014 E-mail: surveyor@surveyors.co.uk |
| 0.5 | ACCESS TO THE SITE | By prior arrangement with the Surveyor |
| 0.6 | DATE FOR RETURN OF TENDER | By 5pm on Friday 26 January 2001 |
| 0.7 | DEFECTS LIABILITY PERIOD | Six Months |
| 0.8 | LIQUIDATED DAMAGES | £3,500 per week |
| 0.9 | CONTINGENCIES | £50,000 |
| 0.10 | ##### INSURANCES | The Contractor shall indemnify the Employer in respect of any liability, loss or claim or proceedings and for any injury or damage whatsoever arising out of or in the course of or by reason of the execution of the said work to any property real or personal due to any negligence, omission or default themselves, their agents or their servants, or to any circumstances within their control with a minimum indemnity limit of £2,000,000 for public liability. |
| 0.11 | SPECIAL INFORMATION | The pre-tender Health & Safety file forms a separate document. Access to the property is through a combination of private, communal and fire escape entrances. These must be fully protected to maintain safe access and egress for the residents. They must be kept clear of obstructions at all times. Due allowance must be made during resurfacing works to the walkways to ensure that access to the immediately affected flats is either maintained or closed off with the prior agreement of the occupiers. |
| 0.12 | ##### CONTRACT ADMINISTRATION | For ease and efficiency and specifically in order to minimise disbursements it is the intention to administer this contract as far as possible, electronically, based on he use of Microsoft Word and Excel software. Accordingly you will have received this specification on a floppy disk or by email. The Form of Tender is to be duly signed and returned as a hard copy in the normal manner. The priced specification is to be returned as a hard copy or as an Excel spreadsheet on disk or by email. All correspondence, issue of instructions, queries etc. will be conducted using email. It is a requirement of this contract that the site office be suitably staffed and equipped to administer the contract electronically. The site office is required to be equipped with a conventional land line with answering machine, e-mail and fax facilities. The contractor will be required to provide bar chart programme using Microsoft Project or similar and to keep it up to date to indicate progress in time for the fortnightly site meetings. Copies of the programme may be made available on the Internet for the information of residents. |

FORM OF TENDER

Ref:  2602

Dear Sirs

Rodney Court Management Limited

# Rodney Court, 6 – 8 Maida Vale, London, W9

Having examined the conditions of contract and specification for works required at the above property, we hereby tender and undertake to carry out and complete the whole of the said works in conformity with the said conditions of contract and specification for the sum of . ....................exclusive of VAT.

We further undertake to commence works on site........weeks after acceptance of our tender and to complete the whole of the works within...............working weeks of commencement on site.

This tender has been prepared in accordance with the Minor Works Building Contract issued by the Joint Contracts Tribunal in 1980 (as amended) and is an agreed lump sum on the understanding that it is accepted within three months from the date stated below.

We agree that unless and until this formal agreement is prepared and executed this tender, together with your written acceptance thereof, shall constitute a binding contract between us.

We understand that you are not bound to accept the lowest or any tender you may receive.

Yours faithfully

Signed			....................................................

For and on behalf of 			..................................................

Address 			...................................................

...............................................

Date 			....................................................